## Sprint2
Date | Points Assigned | Points Completed
2020-01-16 | 18 | 16
2020-01-17 | 39 | 37
2020-01-18 | 12 | 16 | Finished points that were pending)
| 69 | 69

## Sprint1
Task | Sprint 1 | Sprint 2
Create GitHub repository | Completed |  | Ongoing | Completed | Upcoming
Create user stories | Completed
Discuss user stories and order them | Completed
List all user stories on scrum board | Completed
Create a basic layout for the website (tabs + navigation) | Completed
Choose colour palette | Completed
Paragraph on digital governance | Completed
E-governance ranking by country | Ongoing
Paragraph on open government partnerships, links to resources | Completed
Research on Digitalwrapper, maps | Ongoing
Refine design | Completed
Develop a narrative for the website | Completed
Graph 1: Who is spending/How much are they spending on digital governance | Ongoing
Graph 2: What types of projects are they spending on? | Completed
Graph 3: Governments that are leading (ranking chart) | Ongoing
Graph 4: Examples of how users are using it (US govt data) | Ongoing
Choose 4 visualisations (one for each tab) | Ongoing
Create 4 static visualisations | Ongoing
Insert 4 static visualisations onto the pages | Ongoing
Input explanatory text on each page | Ongoing
Create explanatory text for each page | Ongoing
Add title to each graph | Ongoing
Add source to each graph | Ongoing
Change colour scheme | Completed
Change widths of banners | Upcoming
Create header block for web pages | Upcoming
Create text blocks for web pages | Ongoing
Create four image blocks for graphs on home page | Ongoing
Stories onto scrum board | Completed
Add links to data sources for four graphs | Ongoing
Create clickable menu button | Upcoming